## Giai đoạn 1
Week | Goal - Main Tasks | Specific Tasks | Done | Progress | Types | Checkpoint | Notes
Week 1 & 2 | Kick-off & Background Research | Set up environment. Collect the first 10 lectures (videos + slides). | TRUE | Done | Data & Alignment Specialist | Understand project plan. Initialize Git repository. Collect initial reference materials.
|  | Set up environment. Begin comprehensive literature review on RAG, sparse/dense/hybrid retrieval, and multimodal embeddings. | TRUE | Done | Retrieval & Ranking Architect
|  | Set up environment. Begin literature review on RAG frameworks (LangChain vs. LlamaIndex) and prompt engineering for grounded generation. | TRUE | Done | Generation & Application Lead
|  | Begin comprehensive literature review on VLMs, OCRs tools, ASR tools | TRUE | Done | Retrieval & Ranking Architect
Week 3 & 4 | Initial Data Processing & Framework Experiments | Implement a script to extract audio from lecture videos. Run the first ASR experiments with PhoWhisper on 2 lectures. Run OCR trials (e.g., Tesseract, Mistral OCR) on 10 slides. | TRUE | Done | Data & Alignment Specialist | Framework Decision: choose LangChain or LlamaIndex. Initial quality report for ASR/OCR. | 50%. Missing the considerations of multiple options for OCR, ASR => Put this backlog into Week 56 tasks | video -> audio: speed x6
|  | Implement a basic BM25 retriever. Implement a basic dense retriever using a pre-trained Sentence-BERT model. | TRUE | Done | Retrieval & Ranking Architect |  | 50%. Missing code for the Multi-embedding things: colpali or colbert (with the use of Bitsandbyte config) ==> Put this backlog into Week 56 tasks | Dense vs Hybrid nearly the same result but little bit better for Dense
|  | Build “Hello World” RAG apps in both LangChain and LlamaIndex to compare developer experience and features. | TRUE | Done | Generation & Application Lead |  | 80%. Wrong code for the answer generation part. This task only done when this is fixed | Although use the same config for example vector database, splitter, but each types of framework has their own advantages. When done the tasks, show the results for choice later
Week 5 6 7 | Pipeline v1 & Baseline Deployment | Build the reranker to test Reranker vs Non-reranker | TRUE | Done | Retrieval & Ranking Architect | Data Pipeline v1... Retrieval Baselines v1... System Overview... Report Introduction... Components reasoning with comparisons | Build and experiment on top of the Implementation of BM25, Dense and Hybrid Retrieval on Week 34
|  | Using the selected framework, build a unified script to run and evaluate BM25 and dense retrievers on the processed data. | TRUE | Done | Retrieval & Ranking Architect, Generation & Application Lead, Data & Alignment Specialist |  | 50%. Done a part on Week 3 and 4 already
|  | Multi-embedding experiment | TRUE | Done | Retrieval & Ranking Architect |  | Consider Colpali, Cobert, their families, using Bitsandbyte config, comparison
|  | Experiment with database (cloud database) for storage data (embeddings) | FALSE | In Progress | Data & Alignment Specialist, Retrieval & Ranking Architect |  | Move to Week 11 12 | đang thử nghiệm với milvus database cho colbert
|  | Experiment with OCR & ASR. Test some options and pick the better one based on some "criteria", metrics, performance metrics.... | TRUE | Done | Data & Alignment Specialist |  | Experiment with mutliple options: Models vs APIs
|  | Experiment with "Multiple methods" for handling the case of Structural Reports (tables, graphs, charts...) | TRUE | Done | Data & Alignment Specialist |  |  | https://github.com/rednote-hilab/dots.ocr | https://github.com/docling-project/docling
|  | Build a Processor for text (Office docs, multi-format files including Markdown, txt, HTML, URLs, pptx, pdfs), images (slides or images), audio, video | TRUE | Done | Init Implementation |  |  | Those tasks that are thought as cannot be done or cannot be started in these week tasks should be called the backlog tasks and can be moved to be the main tasks of next week tasks
|  | Make the choice with reasoning and explanation for the framework - coding style for our application | TRUE | Done | Generation & Application Lead, Data & Alignment Specialist, Retrieval & Ranking Architect
|  | Think about the "Entities", their fields, flows of the applications --> Preparation Steps for Database Schema | FALSE | To Do | Generation & Application Lead |  | Move to GD2
|  | Create the Overview System Design for the Application --> Including details Layers, Flows and Components | TRUE | Done | Generation & Application Lead
|  | Write the [NOTES] of the Reports on Shared Overleaf | TRUE | Done | Data & Alignment Specialist, Retrieval & Ranking Architect, Generation & Application Lead |  | declaration (ensure that this is our work), acknowledgement (thks for others...), abstract, introduction (motivations, objectives, scope, challenges, structure of the report) | https://www.overleaf.com/project/68ea81a46fb3fd071c383ba7
Week 8 9 10 | Finalize each steps of Pipeline ready for Integration & Report Drafting | Refine the data pipeline (Fix the Processor code). Experiment with pre-/post-processing techniques to improve ASR/OCR quality for visual data | TRUE | Done | Init Implementation, Generation & Application Lead | Thesis Report Draft v1. Finalize each stages of the code, ready for integration.
|  | Refine the embedding and retrieval pipelines into code repo structure (currently the code is just in the notebook only) now we need to convert into code repo | TRUE | Done | Retrieval & Ranking Architect
|  | Create a small evaluation set of 10 questions. Run the baseline retrievers and analyze results using MRR/NDCG/ or some other metrics. Begin writing the “Overview” and “Methodology” chapters of the thesis report. | FALSE | To Do | Data & Alignment Specialist |  | Move to GD2
|  | Develop a UI wireframe. Implement a basic /query endpoint connected to Student B’s retrieval script. Begin writing the “System Design” chapter. | FALSE | To Do | Generation & Application Lead, Init Implementation |  | Move to GD2
|  | Design the core system architecture (API, Databases). Define API endpoints (e.g., /query, /summarize). Begin backend development. | FALSE | To Do | Init Implementation, Generation & Application Lead |  | Move to GD2
|  | Continue to write the report for the [NOTES] part | TRUE | Done | Data & Alignment Specialist, Retrieval & Ranking Architect, Generation & Application Lead |  | Preliminates, Related Works, Our Approach (50%)
|  | Creating the real google form for getting the user choices, opion about our project | FALSE | To Do | Generation & Application Lead |  | Move to GD2
Week 11 12 | Finalizing Thesis Report & Presentation Preparation | Thinking of Chunking and Metadata Strategies | TRUE | Done | Retrieval & Ranking Architect | Final Thesis Report submitted. Presentation slides prepared.
|  | Finalize the Code Flow: Input -> Normalization -> Embedding / Retrieval -> Output Generation | TRUE | Done | Generation & Application Lead
|  | Finalize all code documentation. | TRUE | Done | Data & Alignment Specialist, Retrieval & Ranking Architect, Generation & Application Lead
|  | Database (cloud database) for storage data (embeddings) | FALSE | To Do | Retrieval & Ranking Architect |  | Explore multiple options for this if have time, but we would try to use the common one first for saving time
|  | Finalize the initial implementation docs for reporting | FALSE | In Progress | Init Implementation
|  | Finalize all retrieval experiments and analyses for the report. | FALSE | Done | Retrieval & Ranking Architect
|  | Finalize the Architecture Expected Design for reporting | FALSE | In Progress | Generation & Application Lead
|  | Finish the slides presentation | FALSE | In Progress | Generation & Application Lead
|  | Finish the Report | FALSE | In Progress | Generation & Application Lead |  | Approach - Done cac cau hoi why [done] - Main architecture (components minh su dung) - - vector storage (pending) - - Docling (overview - intro + docling documentation --> summarize --> docling handle multiformat - ocr - vlm - layout...) - - Colpali/Colbert (overview) - - Whisper (overview - GD1) - - ... Intial implementation - FINAL architecture design (pending) - data normalization (check source code project capstone) - data preprocessing (check source code project capstone) - chunking and embedding strategies (pending) - database storage (pending) Evaluation Plan - tham khao anh Lam Future Plan - Overview - BE/FE expected chosen (https://docs.google.com/document/d/1zrs-C04_BdCXsseDV9c6-DrDveUBrt40FEl6pPXlJuE/edit?tab=t.0) - Current tasks - Upcoming tasks + Gantt chart
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE
|  |  | FALSE | FALSE | FALSE

## Giai đoạn 2
Week | Goal - Main Tasks | Specific Tasks | Done |  | Checkpoint | Notes
13 | Phase 2 Kick-off & Integration Planning | Plan to scale data processing to 50+ lectures. Research video–slide synchronization techniques (e.g., MaViLS). | FALSE | Data & Alignment Specialist | Detailed plan and task allocation for Phase 2.
|  | Plan the architecture for full hybrid retrieval, including multimodal embeddings (VISTA) and RRF-based fusion. | FALSE | Retrieval & Ranking Architect
|  | Plan backend and frontend development sprints. | FALSE | Generation & Application Lead
FALSE
14 | Core Module Implementation & Evaluation Dataset Construction | Implement a prototype for video–slide synchronization. Scale up data processing. | FALSE | Data & Alignment Specialist | Joint Task: The entire team collaborates to construct the final evaluation dataset (50+ Q&A pairs).
|  | Implement the multimodal embedding pipeline and load data into the vector store. | FALSE | Retrieval & Ranking Architect
|  | Build the core backend logic for handling multimodal queries. | FALSE | Generation & Application Lead
15 |  |  | FALSE
16 |  |  | FALSE
17 | Hybrid RAG Integration & Frontend Development | Provide synchronized multimodal data chunks to Student B. | FALSE | Data & Alignment Specialist | End-to-end Retrieval Pipeline v1 (not yet optimized) working.
|  | Integrate sparse, dense, and multimodal retrievers with RRF. Deliver a unified retrieval function to Student C. | FALSE | Retrieval & Ranking Architect
|  | Connect the backend with Student B’s retrieval function. Develop core search and result display components on the frontend. | FALSE | Generation & Application Lead
18 |  |  | FALSE
19 |  |  | FALSE
20 | System Evaluation & Thesis Writing | Support data preparation for evaluation. Begin writing Chapter 3 (Data Pipeline) of the thesis | FALSE | Data & Alignment Specialist | Complete System Benchmark results. Draft versions of thesis chapters.
|  | Run the full evaluation on the benchmark dataset. Analyze results for RQ2. Begin writing Chapter 4 (Retrieval System) of the thesis. | FALSE | Retrieval & Ranking Architect
|  | Conduct experiments for RQ3 (faithfulness/groundedness). Analyze results. Begin writing Chapter 5 (Application & Generation) of the thesis. | FALSE | Generation & Application Lead
21 |  |  | FALSE
22 |  |  | FALSE
23 | Finalizing Thesis Report & Presentation Preparation | Finalize all data processing scripts and documentation for Phase 1. | FALSE | Data & Alignment Specialist | Complete Thesis Draft submitted to Supervisor. Demo version finalized.
|  | Finalize thesis chapters and contribute to the Introduction/Conclusion. Prepare the demo script. | FALSE | Retrieval & Ranking Architect
|  | Refine the UI/UX of the web application. Finalize thesis chapters. Lead the creation of the presentation slides. | FALSE | Generation & Application Lead
24 |  |  | FALSE
25 | Thesis Defense | Rehearse presentation. Prepare to answer questions about data processing and synchronization. | FALSE |  | Final Thesis Defense.
|  | Rehearse presentation. Prepare to answer questions about retrieval algorithms and evaluation metrics. | FALSE
|  | Rehearse presentation. Prepare to answer questions about system architecture and prompt engineering. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE
|  |  | FALSE | FALSE